## Workplan
Outreach Tasks |  | Offered Candidates | High Touch Candidates | Medium Touch Candidates | Low-Touch Candidates | Feb. | March | April | May | June | July | August | September | Owner | Sample Tasks | Deadline
| Details | - Candidates have signed their offer letters - Candidates who received an offer letter but have not yet signed | - Candidates for high need subject areas - Candidates who have demonstrated strength in the selection process and interest in the role (high responsiveness, complete selection activities quickly, etc.) - Candidates who were referred by current employees | - Candidates for mid need subject areas who demonstrate solid evidence of potential and are fully eligible - Candidates who express decent interest in the role | - Candidates for low need subject areas - Candidates who may not be eligible for teaching roles - Candidates who are slow to complete selection activities or unengaged in the selection process | March: May
Cultivation Emails | We will have an ongoing series of emails that are sent bi-weekly to keep District A front of mind for candidates. Weekly content will vary, but will include things like a summary of District A's benefits, open positions, highlights about working in this community, and key employement benefits. | X | X | X | X | [9 empty] | Create "Bi-Weekly Highlights" email template | bar: Feb. to September
Create employee value proposition summary and examples to highlight
Map out content for "Bi-Weekly Highlights" email
[15 empty] | Generate list of open positions to include in "Bi-Weekly Highlights" email | Bi-Weekly
[15 empty] | Update "Bi-weekly Highlights" email and send to candidates | Bi-Weekly
Gather media from schools and communities (e.g., pictures from event, staff and student profiles, etc.)
Cultivation Phone Call/Text from District A Teacher | We will call all candidates who receive offers to dicuss details and address questions. We will also call or text high touch candidates to encourage them to continue, answer questions, and support them through the process. | X | X | [11 empty] | Create script for calls with candidates who have received offer letters | bar: Feb. to August
Create script for calls with high touch candidates who haven't gotten to offer stage yet
[15 empty] | Call or text candidates | Weekly/Bi-Weekly
School Visit | We will select small groups of candidates for a school visit and meeting with the District A recruitment team. These will include High Touch candidates, including candidates schools are especially interested in. |  | X | [11 empty] | Determine which schools will be visited | bar: Feb. to May
Create invitation for candidates and school visit agenda
Send invitation to candidates and conduct follow-up communication
Conduct school visits
Interview Support | In order to help fill as many open teacher positions as possible, the recruitment team will assist in scheduling interviews with top candidates during peak staffing season. |  | X | [11 empty] | Create an email template to send to principals that offers support scheduling interviews and requests availability for interviews | bar: Feb. to July
Create an email or phone call template to send to candidates to schedule interviews with principals
[15 empty] | Reach out to ask which positions they need support scheduling interviews for | Weekly
[15 empty] | Schedule interviews with top candidates | Weekly
Referral Support | In order to help fill as many open teacher positions as possible, the recruitment team will ensure that candidate pools are updated regularly and will make targeted referrals for open positions. |  | X | X | [10 empty] | Create a report that matches candidates (based on application data) with openings at schools (based on principal survey data) | bar: April to September
[15 empty] | Use the Principal Survey and report to create referrals for each school | Weekly
Pool Grooming | In order to ensure that the candidates in the pool are viable and still interested in positions with District A, the recruitment team will send a monthly email to all candidates in the pool and require them to indicate whether they are still interested in District A. Those who are no longer available will be removed from the pool |  | X | X | X | [9 empty] | Update template for candidates in the pool to determine if they are still interested in District A, and develop survey for candidates to plug-in information | bar: April to September
[15 empty] | Send email to candidates in the pool | Monthly
[15 empty] | Remove candidates who are no longer interested from the pool | Monthly
Monthly

## Candidate Tracker
Candidate First Name | Candidate Last Name | Source | Date Added | Email Address | Phone | Role Interest | Talent Team Point Person | 1st Follow Up Sent | 2nd Follow Up Sent | Status | Notes
|  | Add candidate source, e.g., LinkedIn, Facebook |  |  |  | Add any notes on the type of role(s) they expressed interest in | Designate a staff member who will own outreach to this candidate | Add the date 1st follow up sent; recommend sending an individualized email encouraging candidate to apply with links to learn more about opportunities, any upcoming information sessions, and the application link | Add the date 2nd follow up sent; recommend sending a quicker follow up email one week after the first if the first outreach does not trigger a response | Use standard terms, e.g., Applied, Not Yet Applied, Not Interested Note: If your ATS supports tracking of prospective candidates, you may use this column to mark who has been entered into your ATS | Add any special notes on candidates